## Sheet1
Platy Manuscript to do:
Goal: Have rough version of main text; have all figures (incl. figure captions, extended data figures), tables, Methods complete by Aug. 2.
Task | Goal | Suggested work plan
Writing
Julia and Danielle to review methods section
Main text draft - send to Julia and Ruth | Get as much progress done before leaving | Work on manuscript consistently (1 hour a day) to push as far forward as possible by Fri Aug 18
Polished draft of the Methods section | Complete by Aug. 2, when Julia returns from KI | Write one subsection of it (i.e. 1-2 paragraphs) each 2 days (e.g. draft 1 day, polish the next day).
Keep working on writing in main text (doing the paragraphs that describe each of the figures first) | progress by Aug. 2 | Suggest to work on this for max. 1 hour per day, when freshest for writing :-)
Data
Re-run bioinformatics pipeline as double check | Needs to be completed before can make Figures 2 or 3. | Plug away at over the new week (i.e. have done by Friday July 21).
Revise all README files in the Git Repo | Completed! | Completed!
Rarify for extended data figure 2 | Complete on Aug 11th (as long as there are no problems) | Danielle to finish after Skype call with Ruth and Julia
Finish up indicator species analysis (check on what else could/should be done with multipatt object) | Complete by Monday, August 14th | Work on starting Aug 11th if I have time, and finish up by Aug 14th at the latest (just need to do some reading about the R package to see if there are any easy additional steps I should add to strengthen this analysis
Figures
Caption for extended figure 2
Re-make extended data figure 2 with rarefied results - Decide whether to keep ex data figure 2
Finish formatting indicator species table for extended data | Complete by Friday, August 18th | Will probably do this before then, while taking a break from writing
Polished version of Figure 1 and caption (i.e. exact formats needed for Nature) | Done!! :-)
Polished version of Figure 2 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Polished version of Figure 3 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Extended Data Figure 1 and caption (i.e. multi-panel photos of ~3 other individul corals (e.g. 3 other species, or 2 other species + a 2nd Platy) | Complete by Aug. 2, when Julia returns from KI | Do when need a break from writing :-)
Extended Data Figure 2 - rank abundance plot (?) showing dominance/evenness of Clade C vs. D (4 panels - low/high disturbance, before/after El Niño) | Complete by Aug. 2, when Julia returns from KI
Fig 2 - put blue dot on top of red dot
Extended data fig 1 - add 3rd column with images of corals ~16 months later
Extended data table 1 caption | Complete by Friday, August 18th | Will probably do this before then, while taking a break from writing
Tables
have a think about if it would be useful to have any other extended data figures or tables in the supp. Mat.
Other
Write cover letter | Draft by Sept 13th, when Danielle returns from honeymoon | Julia/Ruth to write while Danielle is away
Communicate with Ross to set up qPCR | Email sent 8/11
Read more about filamentous algae and fungi