## Sheet1
Platy Manuscript to do:
Goal: Have rough version of main text; have all figures (incl. figure captions, extended data figures), tables, Methods complete by Aug. 2.
Goal: Have a complete rough draft done by Aug 18th, and reviewed by Julia/Ruth (+cover letter written) by September 14th.
Task | Goal | Suggested work plan
Writing
Julia and Danielle to review methods section | Complete by Wednesday, August 16 | Julia review by Aug. 16, and then Danielle and Julia meet on Aug 16 to discuss (that way Danielle can incorporate changes by Friday Aug 18th)
Main text draft - send to Julia and Ruth | Complete by Friday, August 18 | Work on manuscript consistently (1 hour a day) to push as far forward as possible by Fri Aug 18
Revision of main text draft (Julia and Ruth) | Complete by Sept 14th, when Danielle returns from honeymoon | Julia and Ruth review the full manuscript between August 18th and Sept 14th
Polished draft of the Methods section | Complete by Aug. 2, when Julia returns from KI | Write one subsection of it (i.e. 1-2 paragraphs) each 2 days (e.g. draft 1 day, polish the next day).
Keep working on writing in main text (doing the paragraphs that describe each of the figures first) | progress by Aug. 2 | Suggest to work on this for max. 1 hour per day, when freshest for writing :-)
Data
Re-run bioinformatics pipeline as double check | Needs to be completed before can make Figures 2 or 3. | Plug away at over the new week (i.e. have done by Friday July 21).
Revise all README files in the Git Repo | Completed! | Completed!
Rarify for extended data figure 2 | Complete on Aug 11th (as long as there are no problems) | Danielle to finish after Skype call with Ruth and Julia
Finish up indicator species analysis (check on what else could/should be done with multipatt object) | Complete by Monday, August 14th | Work on starting Aug 11th if I have time, and finish up by Aug 14th at the latest (just need to do some reading about the R package to see if there are any easy additional steps I should add to strengthen this analysis
Decide whether unifrac needs to be jackknifed or not | Complete by Tuesday, August 15th | Work on starting Aug 11th if I have time, and finish up by Aug 15th at the latest (need to read up a bit more on this to make sure that we don't need to jackknife the unifrac, and if we do, to ensure I do it correctly)
Figures
Add error bars to figure 2 | Complete by Friday, August 18th | Will probably do this before then, while taking a break from writing
Caption for extended figure 2 | Complete by Friday, August 18th | Will probably do this before then, while taking a break from writing
Re-make extended data figure 2 with rareified results | Complete by Aug 11th (as long as there are no problems) | Danielle to finish after rarifying. If I run into any issues, I will finish this next week.
Finish formatting indicator species table for extended data | Complete by Friday, August 18th | Will probably do this before then, while taking a break from writing
Polished version of Figure 1 and caption (i.e. exact formats needed for Nature) | Done!! :-)
Polished version of Figure 2 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Polished version of Figure 3 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Extended Data Figure 1 and caption (i.e. multi-panel photos of ~3 other individul corals (e.g. 3 other species, or 2 other species + a 2nd Platy) | Complete by Aug. 2, when Julia returns from KI | Do when need a break from writing :-)
Extended Data Figure 2 - rank abundance plot (?) showing dominance/evenness of Clade C vs. D (4 panels - low/high disturbance, before/after El Niño) | Complete by Aug. 2, when Julia returns from KI
Tables
have a think about if it would be useful to have any other extended data figures or tables in the supp. Mat.
Other
Write cover letter | Complete by Sept 13th, when Danielle returns from honeymoon | Julia/Ruth to write while Danielle is away