## Sheet1
Platy Manuscript to do:
Goal: Have rough version of main text; have all figures (incl. figure captions, extended data figures), tables, Methods complete by Aug. 2.
Task | Goal | Suggested work plan
Writing
Polished draft of the Methods section | Complete by Aug. 2, when Julia returns from KI | Write one subsection of it (i.e. 1-2 paragraphs) each 2 days (e.g. draft 1 day, polish the next day).
Keep working on writing in main text (doing the paragraphs that describe each of the figures first) | progress by Aug. 2 | Suggest to work on this for max. 1 hour per day, when freshest for writing :-)
Data
Re-run bioinformatics pipeline as double check | Needs to be completed before can make Figures 2 or 3. | Plug away at over the new week (i.e. have done by Friday July 21).
Figures
Polished version of Figure 1 and caption (i.e. exact formats needed for Nature) | Done!! :-)
Polished version of Figure 2 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Polished version of Figure 3 and caption (i.e. exact formats needed for Nature) | Complete by Aug. 2, when Julia returns from KI | Make week of July 24-28th
Extended Data Figure 1 and caption (i.e. multi-panel photos of ~3 other individul corals (e.g. 3 other species, or 2 other species + a 2nd Platy) | Complete by Aug. 2, when Julia returns from KI | Do when need a break from writing :-)
Extended Data Figure 2 - rank abundance plot (?) showing dominance/evenness of Clade C vs. D (4 panels - low/high disturbance, before/after El Niño) | Complete by Aug. 2, when Julia returns from KI
Tables
have a think about if it would be useful to have any other extended data figures or tables in the supp. Mat.